## TBFF closure protocol
THE THOMAS B. FORDHAM FOUNDATION ACTION PLAN FOR SCHOOL CLOSURE | Organization/individual responsible for executing task* | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
IMMEDIATE ACTIONS
Establish transition team
Define roles, including team leader, faculty point person, parent point person. | Sponsor
Establish weekly date, time and place for team meetings. | Sponsor
Talking points
Establish talking points for dissemination to students/parents, stakeholders, public (press release). | Sponsor
Staff meeting
Establish date and time of staff information meeting to convey news of closure | Governing authority
Parent meeting
Establish date and time of parent meeting to convey news of closure. | Governing authority
Student/parent school choice assistance
Authorizer point person and facutly point person establish date/time/location for student school choice fair(s) | Sponsor
Records security
Ensure that records are in a secure location. Obtain inventory of records. Ensure records are in order and produce transcripts. | Governing authority
Press release
Press release drafted. Incorporate talking points, history of school, reasons for closure, assistance available to parents/staff, authorizer contact information. | Governing authority
Securing the facility
Verify that facility is secure. Obtain list of individuals with access. | Sponsor and governing authority
NOTIFICATIONS
Ohio Department of Education
Send copy of closure notification or governing authority resolution to OCS within twenty four (24) hours of the closure decision. | Sponsor
Staff (teaching and non-teaching)
Written notification. Draft letter to staff. | Governng authority
Include: talking points, reasons for closure, history of school, calendar for remainder of year (timeline for closure), reminder regarding contractual obligations, clarify when benefits end, set forth how to obtain LPDC information, authorizer contact information, transition team contact information. | Governng authority
Notification to staff of meeting. Transition team point person notifies staff of date and time of staff meeting, attendance mandatory. | Governng authority
Staff meeting. Authorizer, board chair and transition team meet with staff within 24 hours of closure decision. Distribute letters. Team and board chair lead discuss content of letters and take staff questions. | Sponsor and governing authority
Calendar. Provide staff with a list of important calendar dates between meeting and end of classes (e.g., grades due, professional development obligations, schedule changes, etc). Ensure that all staff are clear that they should contact the team point person for staff if they have questions. | Governing authority
Parents/guardians
Written notification. Draft letter to parents/guardians. REQUIRED TO BE SENT WITHIN TWO WEEKS** | Governng authority
Include: talking points, brief history of the school, the reason for closure, the school's commitment to parents (e.g., keep things running smoothly until last day, transition assistance for families including information on school choice fairs - or enrollment options and contact information - for parents), records procedures, date of parent information meeting (should be within 24 hours of staff meeting) transition team parent/guardian contact. Letters will be mailed, copies available at parent meeting. | Governng authority
Include parent FAQ. Draft a Frequently Asked Questions document for the general public. Include: talking points, the rationale for closure, when closure will take place, any major changes parents should be aware of before the end of classes, how parents can get help finding a new school, how to request student records, how student records will be handled following the last day of classes, assistance for employees, transition team point person for parents. | Governng authority
Include calendar. List of important calendar dates for parents. | Governng authority
Mail written letter of notification to parents. | Governng authority
Notifications to parents/guardians of parent meeting. Draft postcard and/or flier to mail (may also send home with students) regarding the date, time and location of parent meeting. Note that it is important all parents attend. | Governng authority
Mail (or send with students) notifications (postcard or flier) regarding parent meeting. | Governng authority
Parent meeting. Authorizer, board chair and transition team meet with parents. Disucss contents of parent letter and rationale for closure. Ensure parents know who transition team point person is and have contact information. Take parent questions. | Sponsor and governing authority
Extra copies: have onhand extra copies of a generic parent letter, the FAQ and calendar dates for parents. | Sponsor and governing authority
Media/Public
Post press release on website, forward to local media | Governing authority
Designate authorizer and school point persons for media | Sponsor and governing authority
Transportation
Notify districts that provide transportation at least 30 days prior to closure (or immediately, where necessary). Provide calendar. | Governing authority
Resident Districts
Notify resident districts of closure at least 30 days prior to closure (or immediately, where necessary). Provide calendar (timeline for closure). Provide reasons for closure and sponsor contact information. | Sponsor
Courts
Notify courts for court-placed students. | Governing authority
Data reporting
Schedule a final FTE review within 7 business days with ODE area coordinators | Treasurer
When FTE review is complete, submit a copy of the Certification Form (signed) at the FTE review. | Treasurer
Notify ITC and arrange for all outstanding EMIS data to be reported | Treasurer
Notify ITC and OCS to terminate all SAFE, CCIP and other ODE accounts for personnel associated with the closed school (designated reporting personnel excepted) | Treasurer
Notify STERS/SERS | Treasurer
Notify Auditor | Treasurer
Notifications regarding disposition of property (see also Disposition of Assets) | Treasurer
Notify OCS first, then the media/public. Include date, time and location (e.g., auction). | Treasurer
ONGOING CLOSURE DUTIES
Transition team meetings
Weekly transition team meetings. Agenda should be drafted each week by head of transition team (Authorizer) and forwarded to team prior to meeting. | Sponsor and governing authority
Issues addressed at meeting should include (but not be limited to): recap of events to date; finance update (e.g., issues with inventory, audit, auction, etc); update on tasks in progress; staff (e.g., morale, certification/re-certification issues, the need for substitutes, staff questions, tracking post closure employment opportunities, etc); students and parents (e.g., tracking enrollment, parent questions that require group input, student/parent school choice sessions, securing of records, etc.); outstanding issues; date/time/location of next meeting. | Sponsor and governing authority
Organize parent/student school choice fair(s) REQUIRED TO OCCUR WITHIN TWO WEEKS**
Contact area schools. Notify them of date(s), time(s), location(s) and purpose of school choice fair. Confirm attendance and get name of contact person at each attending school. | Sponsor and governing authority
Finalize list of school choice fair attendees and have transition team faculty point person disseminate to students/parents. | Sponsor and governing authority
School choice fair #1 (date/time/location/attendees) | Sponsor and governing authority
School choice fair #2 (date/time/location/attendees) | Sponsor and governing authority
School choice fair #3 (date/time/location/attendees) | Sponsor and governing authority
Contact each school choice fair participant school and convey thanks for participation. | Sponsor
Staff benefits
Monitor STRS and SERS contributions to make sure they stay current | Treasurer
Get benefits termination and COBRA information to team faculty point person | Treasurer
Staff professional development
Ensure LPDC information is current and available to teachers | Governing authority
RECORDS
School Records
Inventory student records. Student records (including special education) inventoried and put into order. | Governing authority
Ensure transcripts are produced. | Governing authority
Updating student records. The team's faculty point person should work with school staff to ensure that all student records are complete and up-to-date. | Governing authority
Transfer of student records. Contact the relevant districts of residence for students and notify districts of how (and when) records – including special education (which go to the receiving school's special education administrators) - will be transferred. Create a list of all records to be transferred and their destination(s). Transfer remaining records to district following the last day of classes and within seven days of the date of closure, as per ORC 3314.44. | Governing authority
Transfer the records and obtain verification of transfer. | Governing authority
Verification by delivery confirmation (if shipping/mailing records) | Governing authority
Verification by written release (if delivering records in person) | Governing authority
The written release should specify (1) the number of general education records transferred, (2) the number of special education records transferred, (3) the date of transfer, (4) signature and printed name of the charter school representative releasing the records, (5) signature and printed name of the district recipient(s) of the records. | Governing authority
Personnel, non-student and non-personnel records. (For example, financial and staff records.) | Governing authority
Check governing authority records retention policy. Coordinate retention of financial records with treasurer. Coordinate retention of all othe records with governing authority. | Sponsor
Check federal funding sources for grant-specific retention requirements. | Treasurer
FINANCIAL
Closure contingency fund (Y/N)
Weekly balance | Treasurer
Audit
Establish a date for the Auditor of State (or independent accounting firm, whichever applicable) to perform a financial closeout audit within 30 days of closure, while records are onsite. Sponsor retains original records until completion of the audit. | Treasurer
Vendors
Create a list of vendors. Notify vendors that school is closing and work to cancel or non-renew vendor agreements | Treasurer
Disposition of Assets
Fixed assets list. Establish (or update existing) fixed assets list. Keep state and federal dollars separate. Establish checklist of purchasers with proper fund codes (USAS 599, state 001 and 499), the price for each item and identify the source of the funds. | Treasurer
Establish the fair market value (FMV), initial and amortized, for all fixed assets | Treasurer
Disposition of property. Check with state department of education regarding proper procedures for the disposition of property purchased with federal funds | Treasurer
Disposition of inventory. Establish a disposition plan (e.g., auction), and establish a payment process (e.g., cash, checks, credit cards). | Treasurer
Property purchased with Public Charter School Program (PCSP) funds. Property purchased with PCSP funds must first be offered to other community schools with the requisite board resolutions consistent with the purpose of PCSP. If no takers, subsequently auction the propoerty to dispose of assets along with state funded assets. | Treasurer
Auction procedures: (1) notify Office fo Community Schools, then public media, of date and location of auction; (2) Follow EDGAR procedures (34 CFR 80.32) for items $5K or greater; (3) provide board resolutions and minutes of any assets transferred at no cost to another school; (4) provide OCS with a written report of the propoerty and, if available, bill of sale; (5) after taking steps 1-4, any remaining assets may be offered to any public school district with documented board resolutions by the community school and accepting district. | Treasurer
Property purchased with Federal funds: follow EDGAR liquidation procedures, 34 CFR 80.32 (including disposition of items valued $5,000 or greater). | Treasurer
eRate: property/equipment purchased as part of eRate is federal property and cannot be sold as part of the school's assets. For specifics regarding disposition, see http://wwwusac.org/sl/applicants/before-youre-done/equipment-transfer.aspx. | Treasurer
Notification of disposition of assets (e.g., auction). Notify OCS first, then the public (via print and/or radio media). Notice should include the date, location and property to be auctioned. | Treasurer
Price items at fair market value, as determined from inventory and fixed assets policy. | Treasurer
Refund auction proceeds with correct federal and state program codes listed to the appropriate program. Make checks payable to "Treasurer, State of Ohio" | Treasurer
Provide board resolutions and minutes of any transfer of assets with a dollar value of zero (0) to another school | Treasurer
Provide OCS with written report of what sold (bill of sale). | Treasurer
Remaining assets purchased from funds prior to the current USDOE award grant period may be offered to any public school district with documented board resolutions by the community school and the accepting school district. | Treasurer
National School Lunch Program: cafteria equipment purchased with funds from NSLP can only be liquidated via written guidance issued by the Office for Child Nutrition. Contact OCN prior to proceeding with any liquidation. | Treasurer
eTech (state): return to eTech (formerly Ohio School Net) hardware and software acquired with eTech grants. | Treasurer
Disposition of real property (i.e., facilities). Real property acquired from a public school district must be offered to that district's board first, at fair market value. If the district board does not accept the offer within sixty (60) days, dispose of the property in another lawful manner (e.g., auction). | Treasurer
Identify any State Facilities Commission guarantees. | Treasurer
Payment of funds to the state
Pay the following entities, in order, using only foundation dollars and any other non-federal dollars. Consult with counsel if necessary to determine whether there are additional outstanding claims that take precedence (e.g., Medicare, state taxes, worker's comp, city wage taxes). Provide documentation of worker's comp claims, if applicable. | Treasurer
STRS, SERS, retirement and other adjustments | Treasurer
Teachers and staff | Treasurer
Audit preparation | Treasurer
Private creditors or entities with a secured judgment | Treasurer
Forward remaining funds to ODE for redistribution to resident school districts. | Treasurer
If assets are insufficient to pay all persons or entities, prioritization of payment may be determined by the court (see RC 3314.074 and Ch. 1702) | Treasurer
NOTE: Federal dollars can be used to pay teacher and STERS/SERS retuirement costs for any employees who were paid from federal funds when the school was open. Audit costs can be paid from federal funds under certain conditions. Contact the Office of Grants Management for specific guidance before applying any costs against federal funds to support audit costs.
Federal Expenditure Reports (FER) and Annual Performance Report (APR) completed
Ensure that FERS and APRs are complete and submitted to ODE, including Title I. Submit via CCIP. | Treasurer
Itemized financials
Review, prepare and make available the following:
Fiscal year end financial statements | Treasurer
A cash analysis (take previous month recap and determine the cash balance as of closing date) | Treasurer
A list of compliled bank statements for the year | Treasurer
A list of investments in hardcopy | Treasurer
A list of payables (and determine when a check used to pay the liability clears the bank) | Treasurer
A list of all unused checks | Treasurer
Collect and void all unused checks | Treasurer
A list of any petty cash | Treasurer
A list of bank accounts, | Treasurer
Close accounts once all transactions have cleared | Treasurer
A list of all payroll reports including taxes, retirement or adjustments on employee contracts | Treasurer
A list of all accounts receivable | Treasurer
Final Payments and Adjustments
If funds are received after closure, monintor the receipt and adjustments credited to the account of the closed school; determine whether any portion can be applied to satisfy remaining debt; send all or remaining portion to ODE, Office of Policy and Payments, for final dispostion. | Treasurer
SCHOOL CLOSURE ASSURANCES
Submit signed ODE school closure assurances to Office of Community Schools
Sign and submit ODE closure assurances to Ohio Department of Education's Office of Community Schools. | Sponsor
Closure plan is based on guidance from the Ohio Department of Education issued July 2015.
Reprinted with permission of the Thomas B. Fordham Foundation. www.edexcellence.net The Thomas B. Fordham Foundation is neither connected with nor sponsored by Fordham University.
UPDATED 04/2018
*Roles are subject to change as the closure situation merits (including depending on whether a management company is inolved), and at the discretion of the sponsor.
**2017-18 Sponsor Quality Practices Rubric (Deceber 2017) at E.05